## 10 Week
Gantt Chart | [10 empty] | Legends: | Todo | Done | Extended | Cancelled/Delayed
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Notes | Further detail about 1st meetings and initial tasks are in Week 1's Samsung Notes
Literature Review | [11 empty] | This wont just stop at Week 1, but the 3 most important papers emailed to me had been finished read by then
Check and Test GDP code
Evaluate the GDP Code | [11 empty] | Gonna go longer than week 4, hopefully finish analysis with pretty graphs etc by end of Week 5
Transplant Mona's SSC Code | [11 empty] | This is now optional, SSC Mona is using stereo (some problem/setback?)
Test and Evaluate new Code
Wrap-up (Report and presentation)

## Daily report
Week | Monday | Tuesday | Wednesday | Thursday | Friday | Weekly Notes
1 | Induction morning, 1st Meeting with Dr. Hansung Kim, Read AVVR paper, skimmed Mona's Paper, created this excel file. | Read about MDE, SSC, material recognition & mapping, and evaluation metrics from Mona's and GDP report (mostly chapter 2 from GDP). Tested kitchen demo scene on VR headset. | WFH, not much done. Never WFH again! Watched both pipeline and demonstration video from GDP | Read and took notes on chapter 3 (Methodology) and 4 (Results). Experimented a bit on Unity project (test without VR setup). | Cleaned git repo history/merged branches. Created new repo for intern work with separate branch. Fixing broken pipeline due to wsl missing tf2 env and modifying hardcoded directory 'AV-VR' to 'AV-VR-Internship'. ML Pipeline still broken, got value error near the end... | Starting week 2, there's also .docx log in AV-VR-Internship/Intern-Logs folder for each week work, so refer those for more details
2 | Fixed 360monodepth directory issues. Resolved Edgenet360 errors (miniconda, TensorFlow, smoothing). Generated meshes for all scenes. Fixed UnboundLocalError in file_utils.py. Forked and updated Edgenet360/Mesh-generation repo. Planned to rerun and organize outputs. | 2nd meeting with Dr. Kim. Cleaned GitHub repo. Refactored smoothing fix. Generated and imported 5 scene meshes into Unity. Tested audio in VR/non-VR modes. Identified mesh anomalies. Updated TODO list. Regenerated scene meshes with all .obj outputs. | Solved mesh anomaly issue by implementing enhance360.py step. Updated pipeline and GUI.py. Fixed --include-top parameter bug. Explored dynamic ceiling removal methods. Updated TODO list. Tested new mesh generation process on KT and LR scenes. | Added image shifting option to pipeline. Regenerated all scene meshes with/without ceilings. Investigated depth map enhancement issues. Fixed material assignment bug. Updated TODO list. Explored options for improving monodepth output for enhance360 compatibility. | WFH. Read papers. Tested repo pull. Identified issues with submodules and Git LFS. Found ML pipeline broken due to missing submodules. Noted repo size issues (8GB). Planned to remove bloat and fix submodule/LFS problems.
3 | Reviewed TODO list. Investigated depth map enhancement for monodepth. Compared room dimensions from different methods. Analyzed mesh quality and material recognition issues. Encountered pipeline error in GUI.py. | 3rd meeting with Dr. Kim. Updated TODO list. Refactored pipeline for modularity. Debugged file path issues. Investigated Steam Audio settings. Successfully tested KT and MR scenes. Planned further refactoring and optimization. | Updated TODO list. Created new repo to fix git issues. Forked and added submodules. Updated .gitignore for weights/data. Started Phase 2 refactoring to centralize project directory definition. | Tested GUI.py functionality. Explored Steam Audio settings. Experimented with monodepth optimization, focusing on baseline adjustments. Started audio fundamentals study. Simplified depth map enhancement process, focusing on ceiling/floor modification. | WFH. Addressed Unity project issues. Encountered Git LFS bandwidth limit. Updated manual for setup process. Identified potential fix for monodepth optimization using boostingMonocularDepth. Updated TODO list.
4 | 4th meeting with Dr. Kim. Updated TODO list. Fixed Dockerfile build error. Tested BoostingMonocularDepth vs original enhance360.py. Compared depth maps and generated meshes for different scenes. Identified issues with mono depth enhancement. | Reconfigured StartScene with Steam Audio components. Fixed project directory issues. Debugged Steam Audio settings and baking process. Created visualizer script for enhance360.py. Improved fix_limits_mono function for depth map enhancement. | Received MATLAB/Python audio evaluation code. Created helper scripts for model dimension calculation and positioning. Debugged and improved AudioCameraPositioner editor menu. Standardized scene scaling and alignment for 5 evaluation scenes. Updated TODO list. | Organized Unity project folders. Investigated ModelDimension calculation issue. Tested .obj/.mtl import. Explored edgenet library limitations. Noted ST model scaling in Unity. Updated .gitignore. Planned to publish Internship-tools repo. | Updated .gitignore. Investigated Steam Audio settings. Discovered Mesh Dimension Calculator bug. Generated and aligned 5 evaluation scenes. Set up audio sources per S3A settings. Filled dimension table. Established audio baking/export workflow.
5 | Attended Midway Development Day talks. Updated TODO list. Set up audio recording process for evaluation scenes using Audacity and Sony WH1000-XM4 headphones. Adjusted Matlab code for octave band analysis. Prepared RIR file extraction process using Mona's .ipynb code. | Generated all audio. Organized RIR analysis folders. Modified MATLAB scripts for compatibility. Investigated and troubleshooted EDT/RT60 analysis issues. Experimented with different audio settings (sampling rate, sine sweep type, probe number, audio delay, volume). Identified persistent problems with audio analysis results. | Met with Dr. Kim. Reviewed progress and plans. Investigated EDT/RT60 analysis issues. Discovered audio cutoff bug related to Steam Audio initialization. Experimented with various audio settings and recording methods. Identified potential causes for high EDT values. Continued troubleshooting audio analysis discrepancies. | Conducted extensive testing of audio settings across different scenes (KT, MR, ST). Investigated causes of high EDT and RT60 values. Experimented with various mix ratios, volume levels, and Steam Audio parameters. Identified physics-based attenuation as beneficial. Concluded to use Mona's settings with modifications: physics-based attenuation, air absorption, 0.5 volume, and RT60 from extrapolated RT30. Noted limitations in Unity Steam Audio simulation for accurate EDT reproduction. | Week 5 Friday: Resolved Git LFS issues by uninstalling LFS and restructuring repository. Attempted to implement RT30 for RT60 estimation. Encountered difficulties with irStats function parameter adjustments. Experimented with various approaches but faced persistent calculation issues.
6 | Investigated RT30 calculation issues. Discovered limitations in energy decay curve fitting. Revised focus to troubleshoot RT60 problems in Unity. Experimented with various Unity/Steam Audio settings to reduce noise floor level. Tested different volume levels, mix ratios, and HRTF settings. Planned comprehensive review of all related components and settings for further troubleshooting. | WFH. Conducted in-depth review of MATLAB code. Researched related topics to enhance understanding of audio analysis and room acoustics. Prepared for further troubleshooting based on new insights. | Identified critical bug in irStats MATLAB function. Found hardcoded values preventing proper y_fit parameter usage. Tested various RT calculations (RT20, RT25, RT30) on ST scene. Determined RT25 as optimal middle ground. Planned dynamic value adjustment based on y_fit argument for tomorrow. | Modified irStats.m for dynamic value range. Tested various RT calculations across scenes. Identified inconsistencies in EDT and RT60 calculations. Investigated Kim21 and Mona's results. Discovered pre-existing audio files for reference. Revised plan to focus on investigating other MATLAB scripts, verifying older methods, and replicating results with current scenes. | Investigated plotting_rir_compare.m script. Determined older scripts less relevant for current needs. Focused on generating results for each scene. Tuned parameters individually for KT, LR, and MR scenes. Observed persistent issues with noise floor levels and frequency-dependent RT calculations. Planned to complete ST and UL scene analysis next week.
7 | Refined result presentation for easier comparison with Kim21. Created separate scripts for each scene. Reverted irStats.m changes after realizing misunderstanding. Generated new results (v2) for all scenes with adjusted parameters. Observed inconsistencies across octave bands compared to Kim21. Analyzed Mona's latest audio results. Theorized potential limitations in recording method or audio source (sine sweep) as cause for discrepancies. | Met with Dr. Hansung Kim. Discussed ongoing audio analysis issues. Confirmed project details (ceiling inclusion, audio recording method). Implemented direct audio capture in Unity. Created AudioCapture.cs and AudioRecorder.cs scripts. Successfully fixed 4-second audio cutoff issue. Planned to test new recording method on sine sweep for RIR tomorrow. | Successfully tested direct Unity audio recording without headphones. Experimented with various volume levels (0.1 to 1.0) to prevent clipping in KT scene. Adjusted mix levels for direct and reflected sound. Planned to test gunshot and different sine sweep signals. Decided to rewrite parts of analysis .ipynb for new audio sources. | WFH. Conducted research on sine sweep RIR methods. Studied video resources on room acoustics, acoustic measurements, and sine sweep optimization for room impulse response measurements. | Rewrote RIR_Analysis code for new sine sweep signals. Created improved sine sweep generation and deconvolve code in Jupyter notebook. Experimented with various mix ratios and volumes to address clipping and RT60 issues. Observed improvements in octave band responses but encountered persistent challenges with frequency-dependent RT60 values. Considered manual correction for each octave band and explored using smaller y_fit values like RT30.
8 | Reviewed last week's results. Tested various volume levels and mix ratios for KT scene. Improved sine sweep signal with longer duration (15 sec). Observed significant improvements in RT60 and EDT measurements. Identified remaining issues: pre-0s RIR distortion and frequency-dependent RT60 discrepancies. Planned further sine sweep optimization for tomorrow.
9
10