## 10 Week
Gantt Chart | [10 empty] | Legends: | Todo | Done | Extended | Cancelled/Delayed
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Notes | Further detail about 1st meetings and initial tasks are in Week 1's Samsung Notes
Literature Review | [11 empty] | This wont just stop at Week 1, but the 3 most important papers emailed to me had been finished read by then
Check and Test GDP code
Evaluate the GDP Code | [11 empty] | Gonna go longer than week 4, hopefully finish analysis with pretty graphs etc by end of Week 5
Transplant Mona's SSC Code | [11 empty] | This is now optional, SSC Mona is using stereo (some problem/setback?)
Test and Evaluate new Code
Wrap-up (Report and presentation)

## Daily report
Week | Monday | Tuesday | Wednesday | Thursday | Friday | Weekly Notes
1 | Induction morning, 1st Meeting with Dr. Hansung Kim, Read AVVR paper, skimmed Mona's Paper, created this excel file. | Read about MDE, SSC, material recognition & mapping, and evaluation metrics from Mona's and GDP report (mostly chapter 2 from GDP). Tested kitchen demo scene on VR headset. | WFH, not much done. Never WFH again! Watched both pipeline and demonstration video from GDP | Read and took notes on chapter 3 (Methodology) and 4 (Results). Experimented a bit on Unity project (test without VR setup). | Cleaned git repo history/merged branches. Created new repo for intern work with separate branch. Fixing broken pipeline due to wsl missing tf2 env and modifying hardcoded directory 'AV-VR' to 'AV-VR-Internship'. ML Pipeline still broken, got value error near the end... | Starting week 2, there's also .docx log in AV-VR-Internship/Intern-Logs folder for each week work, so refer those for more details
2 | Fixed 360monodepth directory issues. Resolved Edgenet360 errors (miniconda, TensorFlow, smoothing). Generated meshes for all scenes. Fixed UnboundLocalError in file_utils.py. Forked and updated Edgenet360/Mesh-generation repo. Planned to rerun and organize outputs. | 2nd meeting with Dr. Kim. Cleaned GitHub repo. Refactored smoothing fix. Generated and imported 5 scene meshes into Unity. Tested audio in VR/non-VR modes. Identified mesh anomalies. Updated TODO list. Regenerated scene meshes with all .obj outputs. | Solved mesh anomaly issue by implementing enhance360.py step. Updated pipeline and GUI.py. Fixed --include-top parameter bug. Explored dynamic ceiling removal methods. Updated TODO list. Tested new mesh generation process on KT and LR scenes. | Added image shifting option to pipeline. Regenerated all scene meshes with/without ceilings. Investigated depth map enhancement issues. Fixed material assignment bug. Updated TODO list. Explored options for improving monodepth output for enhance360 compatibility. | WFH. Read papers. Tested repo pull. Identified issues with submodules and Git LFS. Found ML pipeline broken due to missing submodules. Noted repo size issues (8GB). Planned to remove bloat and fix submodule/LFS problems.
3 | Reviewed TODO list. Investigated depth map enhancement for monodepth. Compared room dimensions from different methods. Analyzed mesh quality and material recognition issues. Encountered pipeline error in GUI.py. | 3rd meeting with Dr. Kim. Updated TODO list. Refactored pipeline for modularity. Debugged file path issues. Investigated Steam Audio settings. Successfully tested KT and MR scenes. Planned further refactoring and optimization. | Updated TODO list. Created new repo to fix git issues. Forked and added submodules. Updated .gitignore for weights/data. Started Phase 2 refactoring to centralize project directory definition. | Tested GUI.py functionality. Explored Steam Audio settings. Experimented with monodepth optimization, focusing on baseline adjustments. Started audio fundamentals study. Simplified depth map enhancement process, focusing on ceiling/floor modification. | WFH. Addressed Unity project issues. Encountered Git LFS bandwidth limit. Updated manual for setup process. Identified potential fix for monodepth optimization using boostingMonocularDepth. Updated TODO list.
4 | 4th meeting with Dr. Kim. Updated TODO list. Fixed Dockerfile build error. Tested BoostingMonocularDepth vs original enhance360.py. Compared depth maps and generated meshes for different scenes. Identified issues with mono depth enhancement. | Reconfigured StartScene with Steam Audio components. Fixed project directory issues. Debugged Steam Audio settings and baking process. Created visualizer script for enhance360.py. Improved fix_limits_mono function for depth map enhancement. | Received MATLAB/Python audio evaluation code. Created helper scripts for model dimension calculation and positioning. Debugged and improved AudioCameraPositioner editor menu. Standardized scene scaling and alignment for 5 evaluation scenes. Updated TODO list. | Organized Unity project folders. Investigated ModelDimension calculation issue. Tested .obj/.mtl import. Explored edgenet library limitations. Noted ST model scaling in Unity. Updated .gitignore. Planned to publish Internship-tools repo. | Updated .gitignore. Investigated Steam Audio settings. Discovered Mesh Dimension Calculator bug. Generated and aligned 5 evaluation scenes. Set up audio sources per S3A settings. Filled dimension table. Established audio baking/export workflow.
5 | Attended Midway Development Day talks. Updated TODO list. Set up audio recording process for evaluation scenes using Audacity and Sony WH1000-XM4 headphones. Adjusted Matlab code for octave band analysis. Prepared RIR file extraction process using Mona's .ipynb code. | Generated all audio. Organized RIR analysis folders. Modified MATLAB scripts for compatibility. Investigated and troubleshooted EDT/RT60 analysis issues. Experimented with different audio settings (sampling rate, sine sweep type, probe number, audio delay, volume). Identified persistent problems with audio analysis results. | Met with Dr. Kim. Reviewed progress and plans. Investigated EDT/RT60 analysis issues. Discovered audio cutoff bug related to Steam Audio initialization. Experimented with various audio settings and recording methods. Identified potential causes for high EDT values. Continued troubleshooting audio analysis discrepancies.
6
7
8
9
10