## 10 Week
Gantt Chart | [10 empty] | Legends: | Todo | Done
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Notes | Further detail about 1st meetings and initial tasks are in Week 1's Samsung Notes
Literature Review | [11 empty] | This wont just stop at Week 1, but the 3 most important papers emailed to me had been finished read by then
Check and Test GDP code
Evaluate the GDP Code
Transplant Mona's SSC Code
Test and Evaluate new Code
Wrap-up (Report and presentation)

## Daily report
Week | Monday | Tuesday | Wednesday | Thursday | Friday | Weekly Notes
1 | Induction morning, 1st Meeting with Dr. Hansung Kim, Read AVVR paper, skimmed Mona's Paper, created this excel file. | Read about MDE, SSC, material recognition & mapping, and evaluation metrics from Mona's and GDP report (mostly chapter 2 from GDP). Tested kitchen demo scene on VR headset. | WFH, not much done. Never WFH again! Watched both pipeline and demonstration video from GDP | Read and took notes on chapter 3 (Methodology) and 4 (Results). Experimented a bit on Unity project (test without VR setup). | Cleaned git repo history/merged branches. Created new repo for intern work with separate branch. Fixing broken pipeline due to wsl missing tf2 env and modifying hardcoded directory 'AV-VR' to 'AV-VR-Internship'. ML Pipeline still broken, got value error near the end... | Starting week 2, there's also .docx log in AV-VR-Internship/Intern-Logs folder for each week work, so refer those for more details
2 | Fixed 360monodepth directory refs, Edgenet360 fixes: switched to anaconda, updated install steps, fixed TensorFlow ValueError, added checks for IndexError, generated/compared smoothed vs. unsmoothed meshes, fixed UnboundLocalError in Meeting Room scene, forked Edgenet360 to my GitHub, pushed changes. | Prepped for meeting, cleaned GitHub repo, refactored smoothing index error fix, generated 5 scene meshes (KT, LR, MR, ST, UL) and intermediary outputs, tested importing meshes into Unity, used keyboardmove.cs for non-VR testing, noted sound differences, occlusion issues, need to remove anomaly meshes, meeting with Dr. Hansung Kim: advised to keep reading and work on mesh cleanup, updated, modified GUI.py to render without ceiling, regenerated and committed all meshes. TODO: clean up meshes (top and bottom camera occlusion) | Thought about optimal solution, remove anomalies early in pipeline or post mesh generation, noted voxel anomalies linked to floor/ceiling, considered radius-based removal around origin, tested in Blender, found excessive vertices, realized material links missing in Blender, discussed with Mona about enhance360 for depth map, added enhance360.py to pipeline, fixed cone anomaly in meshes, found include_top parameter not working, updated TODOs, learned to verify tools thoroughly, found dynamic height cutoff working for ceiling removal in KT and LR. | Generated scene meshes, noted Docker desktop dependency, MR ceiling material issue fixed by shifting, inconsistent output observed, ST scene correct, proposed pipeline automation for shifting, ceiling removal note, Edgenet360 paper insights on enhance360, compromise in detail loss with enhanced depth maps, UL depth map issue noted, adjusted ceiling cutoff. Shifting improves MR material assignment but needs a stronger depth map. Explore enhance360 and monodepth parameter tweaks. Future work: add more sound options for better UX/UI. | WFH, not much done again. Read papers and tried pulling repo to personal PC. Didn't work yet as missing submodules properly and need git LFS for LiDaR for Unity to work, or exclude the import in the script.
3 | Material assignment inconsistency in UL, add pre-enhancement step for depth map, ensure room dimensions match ground truth or stereo depth map, dimension comparison (HxWxL) for MR, KT, LR, ST, UL, different from ground truth and stereo depth map, KT scaling issue, fits LiDAR scan best, need Dr. Hansung Kim's clarification, experiment with preprocessing steps for better visual results, UL Kim21 import issues in Unity, broken normal map? MR rgb actually already shifted, its height slightly shorter, pipeline lacks object details in final mesh, hinders evaluation, material recognition issues due to cubemap projection limitation, weird filepath error in main GUI.py pipeline, debug tomorrow. | refactored combined.bat to be more modular, fixed bugs, 3rd meeting w/ Dr Hansung Kim, discussed correct dimension scaling, Steam Audio issues, mesh optimization, obtained audio eval code from Mona, tried making monodepth depth map stronger, worked on modular pipeline refactor, fixed pipeline bugs, encountered issues with .jpg and .png files, fixed shifting bugs, tested Steam Audio settings, accessed Steam Audio docs via Wayback Machine, resolved broken pipeline issues, fixed directory path errors, confirmed KT without ceiling works, tested and confirmed MR with ceiling works, need further refactoring for hardcoded directories and temp output removal, Phase 1 refactor complete. | Updated TODO, focused on fixing git repo issues, added LFS, faced issues with remote branch separation, decided to create a new repo, dealt with submodules, forked all related submodules and made them public, faced authorization problems with Vscode, used GitHub Desktop instead, realized I committed weights by mistake, corrected by following ReadMe.md instructions, decided not to fork BoostingMonocularDepth as it's not used, added forked submodules properly with git submodule add, added gitignore for module weights/data, replaced AV-VR directory references, Phase 2 refactor ongoing to centralize main directory definition, committed changes multiple times, will test script functionality tomorrow. | Tested and confirmed GUI.py and Unity project work, focused on Steam Audio quirks, decided to create a fresh Steam Audio project for comparison, noted exact dimension reproduction for monodepth isn't crucial, explored enhance360.py arguments to strengthen depth maps without complex preprocessing, found increasing baseline value helps retain detail, faced issues at baseline 5.264, followed digital audio fundamentals on YouTube, planning to use Audacity for waveform comparison, considered simplifying preprocessing by removing top and bottom modifications only, realized mirror fixes were incidental, commented out plane detection in enhance360.py for better results, but still need to address some depth loss. | Worked from home, cleaned up the GitHub repo for better pulls, faced issues with Unity project .meta files and prefab initialization, ran into Git LFS bandwidth limits due to repeated .obj file pulls, decided to check for .obj file existence before import to avoid errors, planned to use a different storage provider for large files, decided to update the manual with a basic checklist for new PC/system setups, considered reactivating boostingMonocularDepth in 360monodepth for better depth images without enhance360.py, updated TODO to include fixing Steam Audio quirks, optimizing monodepth with boostingMonocularDepth, and removing Docker clutter.
4 | Met with Dr. Hansung Kim at 10:30 am, discussed improving Unity project realism, adding collision for non-VR player controller, implementing binaural audio, and checking RIR calculations. Mona will WFH next week; asked necessary questions and to send recording to Dr. Hansung for feedback. Updated Fixed Dockerfile build error, confirmed Monodepth v1.0 has different Image IDs, refactored code, compared enhance360.py with new enhance360mono.py, found enhance360mono better for depth details but less accurate for room structure. Tested on UL, found MonodepthBoosting not as good as manual edge optimization, generated meshes showed artifacts, MR scene better but not ideal. Plan to generate all scenes and consult Dr. Hansung Kim, identified V2's white balance issue, will figure out monoenhance tomorrow, and may fallback to enhance360.py baseline 2.264. | Reconfigured StartScene to include Steam Audio Probe Batch, added baked source and listener components, changed behavior to baked as per Mona’s recommendation, exported audio using Wavepad or Audacity, added checks and dynamic project directory, confirmed settings with Mona’s suggestions. Found baked settings clearer in directivity and reverb compared to real-time, note to export active scenes after every bake. Encountered bug with old project directory, fixed by reimporting Steam Audio. Baked probe only has one level when using uniform floor mode, requiring player controller with collision for realism. Radeon Rays mode caused OpenCL error, unsure about TrueNext in reflection mode. Baking time should be minimal if correctly configured. Experienced bug with occlusion and distance attenuation in freecam mode. Decided to have an in-game indicator for Steam Audio status. Shifted focus to enhance360mono, created visualizer script, identified fix limits as the issue, promising results with fix_limits_mono from Claude. Signed off for the day.
5
6
7
8
9
10